ASC GROUP

PROPOSAL FOR

AEO T1 OR T2 CERTIFICATE

For FY 2026-27

Date: 27/07/2026

To,

Mr. Satheendran S

Tata Consultancy Services Limited

Powai, Mumbai

Sub: Tata Consultancy Services Limited

Dear Sir,

We ASC Consulting Private Limited (hereinafter referred to as “ASC” or “We”) thank you for the opportunity given to us to submit our scope of work about AEO T1 Or T2 Certificate as applicable to  Tata Consultancy Services Limited (Herein after referred as “Company”).

We understand that the company requires our professional assistance in respect of the aforementioned services for its offices. In this regard, we have stated hereunder the proposed scope of work for your consideration.

With Regards,

Niten Agarwal

Director

For ASC Consulting Private Limited

Scope of Work

In connection to AEO Programme, the following is the SOW drafted;

Scope A- Change of Zone

- Filing of Application for change of Zone from Nhava Sheva to DIC

- Liasioning at Nhava Sheva and DIC

- Addressing departmental queries

- Obtaining NOC from Nhava Sheva for zone change

Scope B- AEO Application

B.1 For AEO-T1

- Compilation of Information/documents required for the purpose of preparing & filing an application

- Preparation & filing of application along with requisite documents in the form of paper-book with AEO Programme Manager

- Preparing and filing the reply against query raised by Custom Department, if any.

- Liasioning with the department and providing explanations as and when needed

- Obtaining approval for AEO-T1 Certification.

B.2. For AEO-T2

- Advisory in relation to the process which would be followed for obtaining AEO Certificate.

- Assisting the company in understanding the whole process of obtaining AEO Certificate.

- Compilation of Information/documents required for the purpose of preparing & filing an application

- Preparation & filing of application along with requisite documents in the form of paper-book with AEO Programme Manager

- Evaluation of existing SOPs.

- Representation & Liasioning before custom department on behalf of the company to explain the background and obtaining initial process, procedures, safety & security related controls/pointers etc. to be maintained which are especially checked by Customs during physical inspection.

- Assist during the Physical Inspection by Custom Department

- Preparing and filing the reply against query raised by Custom Department, if any.

- Liasioning with the department and providing explanations as and when needed

Companies Responsibilities

Company shall be responsible for maintaining & providing below mentioned documents & information:

- Solvency Certificate issued by the Statutory Auditor for the purpose of AEO certification;

- Basic Documents such as COI, IEC, MOA, AOA, PAN, etc.;

- Audited Financial statement & related ROC documents;

- SOPs of the company;

- Document containing detailed security plan;

- Process map illustrating the flow of goods from receipt of order to delivery of products;

- Site plans of all location, and IT security procedures;

- All the necessary information/ documents/ clarifications as required by ASC shall be provided by us from time to time to accomplish the assignment

- Any other document, if required

Professional charges

Considering our new relationship and to invest in it, the professional fees for renewal of AEO T3 certificate is mentioned below;

| Sr. No | Description | Amount (in Rs.) |
| --- | --- | --- |
| 1 | Scope A & T1 application | Rs. 2,40,000 |
| 2 | Scope A & T2 application | Rs. 2,40,000 |

Payment Terms:

- 40% against issuance of PO or signing of agreement;

- 30% against submission of application

- 30% upon completion of the assignment.

Timeline:

- 1-2 months for zone change;

- 3-4 months for T1 from the date of submission of application subject to issuance of deficiencies & officer availability; OR

- 5-6 months for T2 from the date of submission of application subject to issuance of deficiencies & officer availability

Note:

- Fresh SOP drafting & travelling expense for PV, if any shall be charged on additional basis and is not included in the above cost;

- Anything that is not mentioned in the scope of work shall be excluded from this EL;

Cancellation & Refund Clause: In the event the Client chooses to withdraw, discontinue, or cancel the services after commencement of the assignment, or where the assignment is delayed, suspended, rejected, or cancelled due to reasons beyond the control of ASC, including but not limited to non-submission of documents, incorrect information provided by the Client, regulatory changes, actions or decisions of government authorities, or any third-party dependencies, ASC shall not be held responsible for the same and no refund of the advance/professional fees paid shall be made under any circumstances. Further, any work completed, expenses incurred, or additional efforts undertaken, if any till the date of such withdrawal/cancellation shall remain payable by the Client.

If these arrangements are acceptable, please sign one copy of this letter and return it to us.  We trust that our association will be a long and mutually beneficial one.

For Tata Consultancy Services Limited

Name of Authorised Signatory

Designation